## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2211-swen-261-02-4 team4
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | RW;10/26/2021
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | RW;10/26/2021
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | RW;10/26/2021
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | RW;10/26/2021
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | RW;10/26/2021
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | RW;10/26/2021;(Missing implementation) |  | RW;11/1/2021;(Feature now implemented)
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | RW;10/26/2021
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | RW;10/26/2021;(Feature now implemented) |  | RW;11/1/2021;(Feature now implemented)
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | RW;10/26/2021;(Missing implementation) |  | RW;11/1/2021;(Feature now implemented)
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | RW;10/26/2021;(Missing implementation) |  | RW;11/1/2021;(Missing check if a player is already occupied)
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | RW;10/26/2021;(Missing implementation) |  | RW;11/1/2021;(Player is not added to game correctly)
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | RW;10/26/2021;(Pieces are now able to be dragged) |  | RW;11/1/2021;(Feature now implemented)
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | RW;10/26/2021;(Move validation still missing)
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | RW;10/26/2021;(Pieces can now be dropped on open squares) |  | RW;11/1/2021;(Feature now implemented)
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | RW;10/26/2021(Only correctly oriented for red player) |  | RW;11/1/2021(Only correctly oriented for red player)
As a Player, I want to sign out so that I can secure my account after playing a game of checkers. | Given I am on the homepage when I am signed in then I should see a sign out button which I can click. |  |  |  | RW;11/1/2021
| Given I am signed in when I click the sign out button then I should be signed out of my name. |  |  |  | RW;11/1/2021
| Given I am signed out when I am on the homepage then only the number of players online should be shown. |  |  |  | RW;11/1/2021
| Given I am signed out when I am in the homepage then my name should be removed from the list of players. |  |  |  | RW;11/1/2021
As a Player I want my password to be checked when I login so that others cannot log into my account. | Given that a user has put in their password when signing in then they should be signed into their account. |  |  |  | RW;11/1/2021
| Given that a user has put in someone else's password when on the sign-in page then they should not be able to sign-in. |  |  |  | RW;11/1/2021
As a player I want to end the current game so that I can play another game. | Given I am playing a game when I run out of playable pieces then I expect to lose the game
Given I am playing a game when my opponent runs out of playable pieces then I expect to win the game
Given I am playing the game when it is my turn, if I cannot make a legal move then I expect to lose the game
Given I am playing a game when no captures or promotions occur for 40 consecutive turns then I expect the game to draw
Given I am playing a game when the game ends then I should be removed from the game instance and brought back to the lobby screen
As a player, I want to resign so that I can end a game I am losing to deny my opponents the satisfaction of beating me. | Given That I am in a game when I click the resign button then I expect to be removed from the game and given a loss
Given That I am in a game when my opponent clicks the resign button then I expect to be removed from the game and given a win
As a Player I want my piece to become a king and move like a king so that I can gain an advantage for making it to the other side of the board | Given my piece is at the opposing end of the board when I am playing checkers then my piece should become a king.
Given my piece is a king when it is my turn then I should have more possible moves than a regular piece.
Given my piece is a king when it is my turn then I should be able to move that king piece backwards.
As a Player I want to chain the pieces together so that I can come closer to reaching the win condition. | Given I am able to make another capture after capturing a piece when playing checkers then I need to be able to chain in that same turn.
Given I just jumped twice and I see another piece that I can capture when playing checkers then I need to be able to get the next piece.
Given I can jump in two spots when playing checkers then I am able to pick which jump I want to make.
Given that I finished chaining when playing checkers then that only counts as one turn and my turn is over.